## Bug Tracker
Bug ID | Title | Module | Severity | Status | Fix Approach | Wave | Ship / Notes
1 | Clone as draft error 500 | Tender Builder | P0 | FIXED | order field auto-assigned | Shipped v5 | Prod live
3 | Bidding Ops button logs out user | Bidding Ops | P0 | FIXED | Promise.allSettled | Shipped v5 | Prod live
4 | Blank form download PDF fails | Vendor Invites | P1 | FIXED | reportlab fallback | Shipped v5 | Prod live
8 | Invite Vendor not working | Vendors | P1 | CONFIRMED WORKING | User confirmed | N/A | No action
9 | Vendor Add & Fill Full Form 'undefined' toast | Vendors | P1 | FIXED | Defensive undefined fallback | Shipped v5 | Prod live
11 | L1 Comparison Run hangs | L1 Comparison | P0 | FIXED | 45-sec Promise.race timeout | Shipped v5 | Prod live
13 | Masters tab hangs | Masters | P0 | FIXED | Promise.allSettled | Shipped v5 | Prod live
14 | Escrow joint account created without officer info | Escrow | P1 | FIXED | Strict role + email uniqueness | Shipped v6 | Prod live
16 | Budget accepts negative numbers | Notices/Budget | P1 | FIXED | NoticeIn budget_amount ge=0 | Shipped v6 | Prod live
55 | Duplicate of #14 | Escrow | P1 | FIXED | See Bug 14 | Shipped v6 | Duplicate
5 | Notice creation as madhavi shows 'undefined' | Notices (Admin) | P1 | FIXED | reviewer.create=True + defensive notice_ref + role-aware publish | READY v11/v15 | In final zip
22 | Notices form retains previous details | Notices | P2 | FIXED | Full form reset on success | READY v11/v15 | In final zip
23 | Unclear validation toast (10 char min) | Notices Form | P2 | FIXED | Explicit 'Title 3+ chars, Description 10+ chars' | READY v11/v15 | In final zip
24 | Publish checkbox disabled for Master Admin | Notices (Admin) | P1 | FIXED | isMasterAdmin gate | READY v11/v15 | In final zip
46 | Nudge Stale Drafts unclear success | Registrations | P1 | FIXED | Three-branch toast | READY v11/v15 | In final zip
50 | 'clarify recorded' typo + wrong verb | Registrations | P1 | FIXED | Verb mapping | READY v11/v15 | In final zip
28 | Bulk Invite CSV — page blanks / signs out | Vendors — Bulk Invite | P0 | FIXED | Defensive submit + ErrorBoundary | READY v11/v15 | In final zip
36 | Portal hangs on Audit click | Audit | P1 | MITIGATED | ErrorBoundary catches crashes; session preserved | READY v11/v15 | Partial
39 | Generate Award Report page hangs | Evaluation / Awards | P0 | MITIGATED | ErrorBoundary catches crashes; session preserved | READY v11/v15 | Partial
52 | Screen goes blank after bulk invite | Vendors — Bulk Invite | P0 | FIXED | Dup of 28 | READY v11/v15 | Duplicate
57 | Screen goes blank after award report | Awards & POs | P0 | MITIGATED | Dup of 39 | READY v11/v15 | Duplicate
58 | Screen goes blank across flows, requires re-login | General | P0 | FIXED | Root React ErrorBoundary — session preserved | READY v11/v15 | In final zip
43 | Reverse auction Start button doesn't go live | Reverse Auctions | P1 | FIXED | Clearer error naming missing participants | READY v11/v15 | In final zip
44 | Reverse auction Close button doesn't close | Reverse Auctions | P1 | FIXED | Reject close-on-draft + clearer msg | READY v11/v15 | In final zip
51 | No notifications after nudging stale drafts | Notifications | P1 | FIXED | Admin notification per email sent | READY v11/v15 | In final zip
2 | New BOQ template not visible after submission | BOQ Templates | P1 | PARTIAL | Backend list capped + sorted; retest needed | READY v11/v15 | Retest needed
12 | New BOQ contract not showing in list | BOQ Contracts | P1 | PARTIAL | Backend list capped + sorted; retest needed | READY v11/v15 | Retest needed
34 | Product catalog save doesn't persist / not in table | Product Catalog | P1 | FIXED | Cache-buster query param on reload | READY v11/v15 | In final zip
35 | Product catalog created but not in table | Product Catalog | P1 | FIXED | See Bug 34 — same fix | READY v11/v15 | Duplicate
54 | Cancelled meeting still visible | Meetings | P1 | FIXED | Backend hides cancelled by default (include_cancelled param); frontend toggle | READY v11/v15 | In final zip
56 | Rubric saved with values > max / weights invalid | Evaluation | P1 | FIXED | ScoringRubricIn validates weights sum=1.0, max>0, weight in 0-1 | READY v11/v15 | In final zip
G1 | Escrow dual-sig not enforced (same login can sign both) | Escrow | P0-Gov | FIXED | escrow.create_account rejects when pmc_officer.email == escrow_officer.email | READY v11/v15 | In final zip
G2 | COI not cross-checked against committee membership | Evaluation | P0-Gov | ALREADY IMPLEMENTED | evaluations.submit_score blocks if no COI declaration (was already in place) | N/A | Verified in code
G5 | Reverse Auction DRAFT exposes public link | Reverse Auctions | P1 | FIXED | Frontend hides bidder link until status != draft; shows explanatory text instead | READY v11/v15 | In final zip
F1 | Trainee Handbook out-of-date (missing chapters) | Docs | P2 | FIXED | Written PMC_Trainee_Handbook_v3.1.md — 12 chapters covering Roles, RBAC, Permissions Matrix, Notices, Registrations, Bidding/COI, Escrow, Reverse Auctions, Meetings, ErrorBoundary, Help Requests, Portal Branding, bug fix log | READY v11/v15 | Docs delivered
19 | New package created msg but not in list | Packages | P1 | OPEN | Backend + frontend correct on inspection; suspect browser cache. Retest with hard refresh | Retest | Retest first
30 | Newly activated vendor not appearing in Vendors table | Vendors | P1 | OPEN | approve_and_create_vendor sets tenant_id correctly; retest | Retest | Retest first
37 | Duplicate of Bug 19 | Packages | P1 | OPEN | See Bug 19 | Retest | Duplicate
42 | New reverse auction not listed as draft | Reverse Auctions | P1 | OPEN | Backend + frontend correct; may be status filter or cache | Retest | Retest first
45 | Rejected company not shown in Rejected list | Registrations | P1 | OPEN | Backend admin_list filters correctly; verify status enum casing | Retest | Retest first
25 | Withdrawn corrigenda still visible as active | Corrigenda / Notices | P1 | OPEN | Public list filters is_active=True; admin list intentionally shows all with opacity. UX clarification needed | Retest | Clarify UX
26 | Corrigenda status not updated after Withdraw | Corrigenda | P1 | OPEN | See Bug 25 | Retest | Clarify UX
60 | Corrigendum still visible after withdrawing | Corrigenda | P1 | OPEN | See Bug 25 | Retest | Duplicate
6 | Vendor mailing address error persists | Vendor Registration | P1 | OPEN | Need QA screenshot of exact field | Awaiting repro | Awaiting screenshot
27 | Supplier Approve/Reject/Clarify actions not saved | Registrations | P1 | OPEN | Backend updates correctly; retest with hard refresh | Retest | Retest first
29 | Replace Registration Template — undefined toast | Vendors | P1 | OPEN | Need repro from QA | Awaiting repro | Awaiting screenshot
47 | Can navigate past identity section without required fields | Vendor Registration | P1 | OPEN | Section navigation validation needed | Next sprint | Frontend
48 | Unable to download blank registration form | Vendor Registration | P1 | OPEN | Likely dup of Bug 4 (fixed). Verify with QA | Retest | Retest / dup
7 | Resume link not sent to email despite success msg | Vendor Registration / Email | P1 | OPEN | Verify EMAIL_KEY env propagation to Docker | Wave E2 | Verify env
15 | AI Bid Anomaly score/deviation blank | Dashboard | P2 | OPEN | Add 'no anomalies' default state | Wave E2 | Backend + frontend
17 | Error clicking 'Review document' from DocuSign email | DocuSign | P1 | OPEN | DocuSign URL expiry — add retry | Wave E2 | Backend
20 | Check status token — no error for invalid token | Public Landing | P2 | OPEN | Show toast on invalid token | Wave E2 | Frontend
21 | Login shows console error | Login | P2 | OPEN | Need actual console error | Wave E2 | Investigate
31 | Localization incomplete | i18n | P2 | OPEN | Audit i18n JSON files | Wave E2 | Frontend
32 | Profile image not shown after re-login | Profile | P1 | OPEN | TopBar reload on route change | Wave E2 | Frontend
33 | Missing email/mobile validation across forms | Forms (general) | P2 | OPEN | Zod/yup validation | Wave E2 | Frontend
38 | Tender Builder content doesn't update on tab switch | Tender Builder | P1 | OPEN | Reset activeTemplate on tab change | Wave E2 | Frontend
40 | L1 Comparison dropdown empty | L1 Comparison | P1 | OPEN | Filter for awarded bids | Wave E2 | Frontend
41 | Regenerate documents doesn't work | Awards & POs | P1 | OPEN | Add confirmation + version docs | Wave E2 | Backend
49 | Save snapshot to repo — JSON parsing error | Stakeholder Reports | P2 | OPEN | Wrap in try/catch, return JSON error | Wave E2 | Backend
G3 | Two access-control systems (Permissions vs Level) | Governance | P1 | PARTIAL | Documented in Handbook chapter 1; full consolidation deferred | Wave G2 | Docs done, code TBD
G4 | Stakeholder Reports doesn't match description | Reports | P1 | OPEN | Product decision — rename or rebuild | Wave G2 | Product decision

## Summary
Status | Count | Notes
FIXED / SHIPPED | 27 | Live in prod OR in v11/v15 zip OR verified in existing code
MITIGATED | 2 | ErrorBoundary catches; full underlying fix pending
PARTIAL | 3 | Root cause mitigated; needs retest
OPEN | 24 | Awaiting retest OR needs more repro info
Deploy plan for v11/v15
1. Deploy pmc-backend-v11-final.zip to EB
2. Upload pmc-frontend-v15-final.zip to S3 + CloudFront /*
3. QA retest ALL bugs marked 'READY v11/v15' (28 items)
4. Verify 'OPEN' bugs marked 'Retest first' — many may resolve after hard refresh
5. Wave E2 remaining (12 misc bugs) + G2 governance (2 items) in next sprint