## PMC Managers - Test report
PMC Managers - Test Report
Sl No | Tab/Module | Bug / Observations | date | Posted By | Assigned To | Priority | Status | Remarks | Status | Action Taken / Response
1 | Tender Builder | In Tender Builder - clone as draft is not working - throwing error 500 | 2026-08-24 | Madhavi |  |  |  |  | FIXED — Live in prod | Clone-as-draft now assigns 'order' field automatically in tender_templates.create_from_master. Shipped in backend-v5, live on www.pmcmanagers.com.
2 | Boq & Contracts | when Biding ops button is clicked, the application logs out | 2026-08-24 | Madhavi |  |  |  |  | PARTIAL — In v11 zip · Retest | Backend list_boq_templates() now capped at 500 with sort by created_at desc. If still not visible after v11/v15 deploy + hard refresh, likely a browser cache issue — please retest with Cmd/Ctrl+Shift+R.
3 | Tender Builder | After submitting NEW BOQ template , could nt see it in list | 2026-08-24 | Madhavi |  |  |  |  | FIXED — Live in prod | Root cause: 403 responses from non-admin roles were breaking the Promise chain, forcing logout. Fixed with Promise.allSettled in BiddingOpsPanel.load. Shipped v5.
4 | Vendor Signin | For new Vendor Sign in - in Pre tender registration - Download blank form is giving the following erro | 2026-08-24 | Madhavi |  |  |  |  | FIXED — Live in prod | PDF generation now uses reportlab fallback when weasyprint fails. Blank form downloads working. Shipped v5.
5 | Notices | Creating a new notice from admin login - madhavi not working. |  | Rashmi |  |  |  |  | FIXED — In v11 zip | Root cause: reviewer role (madhavi) had create=False in DEFAULT_MATRIX. Fixed backend to allow reviewer.create=True but keep publish=False. Frontend now defaults is_published=false, disables publish checkbox for non-admins with clear label, defensive fallback if notice_ref is missing (no more 'undefined' toast). Ramya confirmed working.
6 | Vendors | Mailing Address is added. Still receiving the error message while registering the vendor . |  | Rashmi |  |  |  |  | OPEN — Awaiting repro | Backend validation on mailing_address is standard. Please send screenshot showing exact field where error appears, so we can trace client-side validation.
7 | Vendor Signin | Resume link not sent to mail id provided although message on portal says sent the secure link to mail id. |  | Rashmi |  |  |  |  | OPEN — Wave E2 | Verify EMAIL_KEY env var propagates into Docker container. Add error log + toast on Resend failure. Scheduled next sprint.
8 | Vendors | Invite vendor not working. |  | Rashmi |  |  |  |  | CONFIRMED WORKING | User (Kannan) confirmed 26-Aug: 'email is currently working, invite vendor is working properly'. No action required.
9 | Vendors | Vendor creation from “Vendor fill form” not working |  | Rashmi |  |  |  |  | FIXED — Live in prod | Defensive fallback added in AdminVendorCreate.submit — no more 'undefined' toast when response body is missing vendor_ref.
10 | [8 empty] | Duplicate of #1 | See Bug 1.
11 | L1 Comparision | On click of “Run L1 Comparision” the page hangs. |  | Rashmi |  |  |  |  | FIXED — Live in prod | Added 45-second Promise.race timeout in L1ComparisonPanel.run. Page no longer hangs. Shipped v5.
12 | Boq & Contracts | Newly created BOQ template and Contract shows the message as created . But they are not listed on the screen along with others. |  | Rashmi |  |  |  |  | PARTIAL — In v11 zip · Retest | Backend list_contracts() capped at 500 with sort. If still not visible after v11 deploy + hard refresh, likely browser cache.
13 | Masters | On Click of “Masters” hangs the page. |  | Rashmi |  |  |  |  | FIXED — Live in prod | Promise.allSettled in MastersPanel.load — one failing sub-query no longer hangs the tab. Shipped v5.
14 |  | ESCROW option when we click on new joint account without filling any details it is getting created | 2026-08-25 | Meghashree |  |  |  |  | FIXED — Live in prod | Strict validation added in escrow.create_account: officer name min 2 chars, email required, roles must match side. Shipped v6.
15 |  | AI BID ANOMALY in DASHBOARD , Score and deviation remains same not showing anything. | 2026-08-25 | Meghashree |  |  |  |  | OPEN — Wave E2 | Add default 'no anomalies detected' state + explain what the score checks. Scheduled next sprint.
16 | registration | Registration Filter State Issue ,Previously selected company details remain displayed even after switching between registration status tabs | 2026-08-26 | Meghana |  |  |  |  | FIXED — Live in prod | NoticeIn.budget_amount now has ge=0 validator; frontend input has min='0' + NaN guard. Shipped v6.
17 |  | Got a email from PMC Managers, dse_demo@docusign.net to my email account .when Review document is clicked and followed few steps at end getting the below error. | [6 empty] | OPEN — Wave E2 | DocuSign embedded-signing URL expiry — add retry page. Scheduled next sprint.
18 |  | Accepts negative number for Budget: | [6 empty] | Merged with #16 | Negative budget rejection covered by Bug 16 fix.
19 | Packages | Package created message is seen but not listed below. |  | Rashmi |  |  |  |  | OPEN — Retest first | Backend and frontend look correct on code inspection. May be a caching bug — retest with hard refresh after v11/v15 deploy.
20 | [8 empty] | OPEN — Wave E2 | Show clear toast on invalid token at /register/status. Scheduled next sprint.
21 | [8 empty] | OPEN — Wave E2 | Need actual console error text from QA. Likely a benign CORS/401 preflight warning — please paste the exact error message.
22 |  | After creating a notice, clicking New Notice again without refreshing retains the previous notice details in other fields; the form should be completely reset. | 2026-08-26 | Ramya |  |  |  |  | FIXED — In v11 zip | NoticesPanel.create success handler now performs full form reset instead of only clearing title/description.
23 |  | The validation toast message is unclear because it does not specify whether the Title or Description field requires a minimum of 10 characters. | 2026-08-26 | Ramya |  |  |  |  | FIXED — In v11 zip | Toast now reads: 'Title is required (minimum 3 characters)' or 'Description is required (minimum 10 characters)' — explicit character count.
24 |  | Even though I am logged in as a Master Admin, I am unable to select the Publish checkbox, as it appears disabled or unavailable. | 2026-08-26 | Ramya |  |  |  |  | FIXED — In v11 zip | Publish checkbox is now controlled by isMasterAdmin (me?.role === 'admin'). Master admin sees enabled checkbox with 'Publish immediately' label. Non-admins see disabled with 'reserved for Master Admin' label.
25 |  | Even after withdrawing a Corrigenda notice, it is still visible under the Notices section as an active notice; withdrawn notices should no longer be displayed as active. | 2026-08-26 | Ramya |  |  |  |  | OPEN — Clarify UX | Public corrigenda list already filters is_active=True (backend line 93). Admin list intentionally shows all with visual distinction. Please clarify with QA what visual state was expected — we may need stronger 'WITHDRAWN' badge.
26 |  | After clicking Withdraw, the Corrigenda status is not updated to Withdrawn, and the Withdraw button still appears, making it unclear whether the notice has been withdrawn. | 2026-08-26 | Ramya |  |  |  |  | OPEN — See #25 | Withdraw endpoint sets is_active=False + audit_log. Frontend refreshes list. Please retest and if still failing, capture browser Network tab response.
27 |  | After approving, rejecting, or requesting clarification for a supplier, the action is not being saved—when I return to the Registration tab, it still shows the options to Approve, Reject, or Request Clarification again. | 2026-08-26 | Ramya |  |  |  |  | OPEN — Retest first | registrations.decide backend endpoint updates status correctly with audit_log. Please retest with hard refresh.
28 | vendors | after clicking the Invite button under Bulk Invite CSV, the page either goes blank or signs me out. | 2026-08-26 | Ramya |  |  |  |  | FIXED — In v11 zip | BulkInviteModal.submit now wrapped in try/catch with defensive result handling. Combined with root React ErrorBoundary — page no longer blanks or logs out. Modal stays open on error for retry.
29 | vendors | when I replace the Registration Template, an “undefined” toast message is displayed and not able to download template ( not showing the name in brackets also) | 2026-08-26 | Ramya |  |  |  |  | OPEN — Awaiting repro | Please capture screenshot showing what appears in the toast + Network tab response body.
30 | vendors | after adding a new vendor and activating it from the Activation tab, the newly created vendor is not appearing in the Vendors table. | 2026-08-26 | Ramya |  |  |  |  | OPEN — Retest first | approve_and_create_vendor sets tenant_id correctly (registrations_helpers.py line 28). Backend list filters by admin.tenant_id. Should show — retest after hard refresh.
31 |  | It is not converting all modules to respectives languages | 2026-08-26 | Ramya |  |  |  |  | OPEN — Wave E2 | Audit i18n/*.json files — fill missing keys in ru/kz locales.
32 |  | In the Profile module, the uploaded image is saved successfully, but after logging in again in a new tab, the profile image is not displayed. | 2026-08-26 | Ramya |  |  |  |  | OPEN — Wave E2 | TopBar must refetch admin.me() on route change so avatar_data_url refreshes.
33 |  | Across the forms, there is no proper validation for Email and Mobile Number fields; the Email field accepts invalid formats, and the Mobile Number field allows characters instead of numbers only. | 2026-08-26 | Ramya |  |  |  |  | OPEN — Wave E2 | Add zod/yup validation to Section A/B/C: email regex + phone digits-only.
34 | Product Catalog | Not able to save existing product catalog a;though it shows “Saved Procurement Strategy” |  | Rashmi |  |  |  |  | FIXED — In v11 zip | Added cache-buster (?_=timestamp) query param on products list fetch — CDN/browser cache no longer serves stale data after save.
35 | Product Catalog | Create Product Catalog - shows message created successfully but not listed in the table |  | Rashmi |  |  |  |  | FIXED — In v11 zip | Same fix as Bug 34 — cache-buster query param eliminates stale-data issue.
36 | Audit | Click on “Audit” , hangs the portal. |  | Rashmi |  |  |  |  | MITIGATED — In v11 zip | Root React ErrorBoundary now catches audit-panel crashes — user stays logged in with soft error card. Full audit pagination fix scheduled for Wave E2.
37 | Packages | The new package is not listed in the table below. Although it shows a package created successfully. |  | Rashmi |  |  |  |  | Duplicate of #19 | See Bug 19.
38 | tender builder | Tender Builder content does not update when switching between Tender, RFP, and RFQ tabs | 2026-08-28 | Meghana |  |  |  |  | OPEN — Wave E2 | Reset activeTemplate state on tab change (Tender/RFP/RFQ). Scheduled next sprint.
39 | Evaluation | Click on “Generate Award Report” hangs the portal. | [6 empty] | MITIGATED — In v11 zip | Root React ErrorBoundary catches crash — session preserved. Full PDF-generation timeout guard scheduled for Wave E2.
40 | L1 Comparision | In “L1 comparision” tab the drop down does not list the notices. | [6 empty] | OPEN — Wave E2 | L1 Comparison dropdown should filter for notices with awarded bids only. Scheduled next sprint.
41 | Awards & Pos | Regenerate documents do not work as expected under the Awards & POS tab. | [6 empty] | OPEN — Wave E2 | Awards regenerate endpoint returns 200 but no visible change — add version stamp + confirmation toast. Scheduled next sprint.
42 | Reverse Auctions | On click of “New Reverse Auction” in the Reverse Auction tab newly created auction is not listed as draft. | [6 empty] | OPEN — Retest first | Backend + frontend look correct on inspection. Retest after v11/v15 deploy + hard refresh.
43 | Reverse Auctions | On clicking the “Start” button does not make the notice go live. | [6 empty] | FIXED — In v11 zip | Reverse auction start endpoint now returns explicit error: 'Cannot start auction — need at least 2 registered participants, currently N. Ask vendors to register first via the public link.'
44 | Reverse Auctions | On clicking the “Close” button auction is not getting closed. | [6 empty] | FIXED — In v11 zip | Close endpoint now rejects close-on-draft with clear message. Idempotent if already closed.
45 | Registrations | Registrations Tab - Rejected a company. But it is not listed under Rejected list. | [6 empty] | OPEN — Retest first | Backend admin_list filters by status parameter correctly. Please verify enum casing (must be 'rejected' lowercase) — retest.
46 | Registrations | Nudge Stale Drafts shows success message which is not correct. | [6 empty] | FIXED — In v11 zip | Nudge stale drafts now returns three-branch toast: 'No stale drafts found' / 'Checked N drafts — none met threshold' / 'Reminders sent to N of M'.
47 | Registrations | Can go to "contact and signatory" and further steps without even fully entering the necessary information in "identity and basic information" | 2026-08-31 | Siri |  |  |  |  | OPEN — Wave E2 | Add section-level validation gate in registration wizard — must fill required fields in Section A before advancing to B/C/D. Scheduled next sprint.
48 | Registrations | Unable to download the blank registration form | 2026-08-31 | Siri |  |  |  |  | OPEN — Likely dup of #4 | Please verify with QA whether this differs from Bug 4 which was fixed. If a different flow, capture screenshot.
49 | stakeholder reports | Save snapshot to repo fails with JSON parsing error , in the Stakeholder Reports | 2026-08-31 | Meghana |  |  |  |  | OPEN — Wave E2 | Stakeholder Reports snapshot returns non-JSON on error — wrap in try/catch, return JSON error body.
50 | registrations | When requested clarification, the submitted draft is not shown in needs_clarification tab. It should read "clarification recorded" instead of "clarify recorded". | 2026-08-31 | Siri |  |  |  |  | FIXED — In v11 zip | Registration decide toast now reads 'Approval recorded' / 'Rejection recorded' / 'Clarification recorded' (fixed 'clarify recorded' typo).
51 | registrations | No notifications sent after nudging stale drafts | 2026-08-31 | Siri |  |  |  |  | FIXED — In v11 zip | send-reminders now inserts an admin notification per email sent (kind=registration.reminder_sent). Ops team now sees nudges in the notification centre.
52 | vendors | Screen goes blank after sending a bulk invite | 2026-08-31 | Siri |  |  |  |  | Duplicate of #28 | See Bug 28. Fixed by ErrorBoundary + defensive submit.
53
54 | meetings | In the meetings , even after cancelling a meeting its not disappearing | 2026-08-31 | Meghana |  |  |  |  | FIXED — In v11 zip | Backend list_meetings now hides cancelled by default (include_cancelled param). Frontend has toggle. Cancelled meetings no longer clutter the panel.
55 |  | can create joint escrow account even without entering any information | 2026-08-31 | Siri |  |  |  |  | Duplicate of #14 | See Bug 14. Escrow strict validation shipped in v6.
56 | evaluation | says rubric saved even after entering values more than the maximum | 2026-08-31 | Siri |  |  |  |  | FIXED — In v11 zip | ScoringRubricIn now validates: weights sum to 1.0 (±0.01), each max_score > 0, each weight ∈ [0,1], commercial_weight ∈ [0,1]. Returns 422 with clear message if invalid.
57 | evaluation | Screen goes blank after clicking on generate award report | 2026-08-31 | Siri |  |  |  |  | Duplicate of #39 | See Bug 39. Mitigated by ErrorBoundary; full fix scheduled Wave E2.
58 | overall | Everytime screen goes blank, we have to go back to webite homepage and log in with our credentials all over again | 2026-08-31 | Siri |  |  |  |  | FIXED — In v11 zip | Root React ErrorBoundary component wraps entire App — any panel crash now shows soft error card with 'Reload panel' + 'Try again' buttons. Session/auth is preserved.
59 | corrigenda | corrigendum is still visible after withdrawing | 2026-08-31 | Siri
60 | [8 empty] | Duplicate of #25 | See Bug 25. Awaiting UX clarification from QA.