## Asked vs Delivered
# | Status | Area | What was asked | What has been delivered | Notes / Evidence
1 | Delivered | Auth & Access | Multi-role staff + vendor authentication with MFA | HTTPOnly cookie auth + CSRF, TOTP MFA, Unified Two-Card Login Hub, staff/vendor/admin flows | Waves 1-14 · MFA verified via TOTP
2 | Delivered | Auth & Access | Role-based permissions across staff (Escrow, Certifier, Legal, Accounting…) | Dynamic Permissions Matrix panel, per-endpoint role decorators, audit logs on every action | PermissionsPanel + `security.require_role`
3 | Delivered | Multi-tenant | Portal skinning per tenant, CNAME-based routing | CNAME multi-tenant subdomains, tenant chip on admin bar, per-tenant branding colour + logo | Wave 22 · `tenants.by-host` + `useTenantSkin`
4 | Delivered | i18n | Trilingual UI (English, Russian, Kazakh) | Full EN/RU/KK dictionary, live switcher, localised country dropdown | Wave 19 · `i18n-strings.js`
5 | Delivered | Notice Board | Public tender board with document downloads | Public notice list + detail pages, primary document, attachments, deadline | `notices` router + `NoticeDetail.jsx`
6 | Delivered | Vendor Registration | 5-section vendor registration (A-E) with KYC document slots | Sections A-E form, magic-link resume, per-slot document upload, admin "add & fill on behalf" | Wave 14 · `RegistrationResume` + `DocSlot`
7 | Delivered | Vendor Registration | Silent draft creation so admins can upload docs without an extra click | `ensureDraft()` auto-saves the record the moment an admin picks a file | Wave 27
8 | Delivered | Tender Builder | Template builder mirroring a real 39/75-page PSU tender | 18-section master template (Sections 1-4, Annexures I-VIII, Forms A-F), clone-to-draft | Wave 20 · `TenderBuilderPanel`
9 | Delivered | Tender Builder | Structured CPPP-style tender header (dates, EMD, budget, authority) | Full `TenderHeaderForm` — Basic Details, Cover Details, Fee & EMD, Critical Dates, Authority (~60 fields) | Wave 24
10 | Delivered | Tender Builder | Rich formatting for section bodies | Dependency-free RichEditor (Bold/Italic/H2/H3/lists/quote) with DOMPurify sanitisation on ingress + egress | Wave 24 + 25 (XSS hardened)
11 | Delivered | Tender Builder | Per-section attachment upload (blank annexure forms) | Upload/Replace/Remove per section, served through the uploads router with proper filenames | Wave 24 + 26
12 | Delivered | Tender Builder | Bulk drop many blank forms and auto-match to sections | Multipart endpoint + fuzzy matcher (annex-VIII_bank.pdf correctly matches annex-VIII, not annex-V) | Wave 29
13 | Delivered | Tender Builder | Version history + one-click revert | 20-snapshot rolling versions, dedicated drawer UI, restore is itself auto-snapshotted (undoable) | Wave 31
14 | Delivered | AI Copilot (advisory) | AI-assisted section drafting | Per-section ✨ menu with tone (Formal/Plain/Strict) × length (Short/Medium/Long) knobs, HTML output, bleach-sanitised | Waves 29-30 · LLM Key
15 | Delivered | AI Copilot (advisory) | Compare bids and surface clause-level differences | `/api/v1/bids/compare-ai` returns `summary`, `clauses[]`, `recommended_questions[]`, `advisory_notice`; refuses to name a winner | Wave 31 · human retains signature
16 | Delivered | AI Copilot (advisory) | Show a diff before overwriting a section that already has content | `AiDiffModal` with word-level red/green diff and +N/−N stats | Wave 30
17 | Delivered | AI Governance | AI stays advisory; humans keep signature | Every AI endpoint carries an advisory notice, no automated state changes, full audit_log entries | Architecture guardrail 2026-08-03
18 | Delivered | PDF Export | One-click composed tender PDF from Notice detail | WeasyPrint server render, `Content-Disposition: attachment`, real %PDF-1.7 | Wave 28
19 | Delivered | PDF Export | Watermark + version stamp on every page | Diagonal DRAFT watermark, top-right tender ref, bottom footer `status · v{n} · issued yyyy-mm-dd · Page x/y` | Wave 29
20 | Delivered | PDF Export | Multi-language toggle (EN / RU / KK) | `?lang=` param on `/export/pdf` and `/public/pdf`; static labels + watermark localised, bodies unchanged | Wave 31 · pypdf-verified for RU
21 | Delivered | PDF Export | Bundle the PDF + every section attachment into a single .zip | `/public/zip?notice_ref=…` uses `zipfile` stdlib, includes README.txt index | Wave 30
22 | Delivered | Bidding | Multi-role approval pipeline (Escrow → Admin → Certifier → Legal → Accounting → Committee) | Dynamic Approval Matrix per notice or falls back to default; committee panel + inspections + tasks | Waves 1-2
23 | Delivered | Bidding | Public clarifications thread on the Notice page | `notice_qa` router — bidders ask, admin replies, only answered pairs shown publicly with masked emails | Wave 31
24 | Delivered | Compliance | KYC as a pre-bid gate — verify before allowing bid submission | `bids.create_bid()` returns HTTP 412 unless vendor has a passing KYC decision; `kyc_bypass` override on notices | Wave 35d
25 | Delivered | Escrow (EMD) | EMD held in an escrow-controlled account, not a PMC operational account | Joint escrow accounts with TWO named officers (one PMC, one escrow institution) on file | Wave 32
26 | Delivered | Escrow (EMD) | Release requires dual authorisation from both operating officers | `/transactions/{id}/sign` per officer + `/release` gated by both signing the same action; 409 otherwise | Wave 32 verified via curl
27 | Delivered | Escrow (EMD) | Three outcomes: to contractor (via PMC), refund to vendor, forfeit | `release_to_contractor` / `release_to_vendor` / `forfeit` — all audit-logged and immutable on tx | Wave 32
28 | Delivered | Escrow (EMD) | Non-PMC escrow officer signs without a full staff account | `POST /escrow/magic-tokens` admin-issued token → `/escrow/officer/:token` public portal signs the same transactions | Wave 35b
29 | Delivered | Revenue Catalog | Admin-editable master of every revenue line (client + supplier) | 55 products seeded from CA-02/CA-03; 9 pricing models; multi-currency; live CRUD via Admin → Product Catalog | Wave 35 · `products.py`
30 | Delivered | Revenue Catalog | Client purchase surface — packages + services | Public `/services` with 34 products, 5 category filters, quote-vs-subscribe CTAs driven by pricing_model | Wave 36 · `ClientPurchase`
31 | Delivered | Revenue Catalog | Quote pipeline — Request quote → engagement → admin quote → invoice → paid | New `engagements.py` router + `EngagementsPanel.jsx` admin UI. Quote requests from purchase pages land in a persistent pipeline; admin sets amount, generates Stripe pay-link in one click; end-to-end tested $40k USD. | Wave 38
32 | Delivered | Revenue Catalog | Supplier purchase surface — Supplier Success + tender-stage + add-ons | Public `/vendor/services` with 21 products, GBP pricing, SME/Mid/Tier-1 subscription tiers | Wave 37 · `VendorPurchase`
33 | Delivered | Payments | Stripe Checkout for one-off + subscription products from the catalog | `POST /api/v1/billing/checkout` (admin, vendor OR anon) creates `cs_test_...` session with server-authoritative amount; `/api/webhook/stripe` idempotent | Wave 35 · `pmc_lib`
34 | Partial | Payments | PayPal, Kaspi Pay | In sandbox mock — waiting for merchant credentials | P2 · blocked
35 | Delivered | Evaluation | Committee scoring with per-criterion weights | Evaluation panel with rubric management, external committee invite by email, accept-flow | Waves 2-5
36 | Delivered | Contracts / BOQ | BOQ Builder + Contract Award workflow | BOQ/Contracts panel, BOQ templates, contract award pipeline | Waves 3-4
37 | Delivered | Audit | Every substantive action is logged and attributable | Global `audit_log` collection + per-transaction immutable `audit_trail[]` on escrow records | Throughout
38 | Delivered | Governance | Live public roadmap page so vendors can see what's built vs coming | Public `/roadmap` reads `/api/v1/reports/public/roadmap` — 20 areas, status pills, stat-card filters | Wave 35c
39 | Delivered | Governance | Stakeholder reports auto-regenerate on every deploy | `_refresh_reports_snapshot()` runs at startup — `/app/docs/reports/*.{xlsx,docx,pdf,svg}` never drifts | Wave 35e
40 | Delivered | Mobile | Mobile-friendly app for staff and vendors | PWA + Capacitor mobile wrapper, unified `/m` login, mobile hamburger menu | Waves 13, 22
41 | Delivered | Legal | PKI / DSC (Digital Signature Certificate) integration for bid + contract signing | DocuSign eSignature via JWT Grant (sandbox). New `/api/v1/docusign/*` router — envelope creation from Award PDFs (PO/SLA/Contract) + Bid acknowledgements, embedded signing view, Connect webhook for status. Admin DocuSignPanel with consent flow + envelope log. Trilingual (EN/RU/KK) | Wave 43 · consent granted, sandbox live
42 | Delivered | i18n | Trilingual coverage across every admin panel (not just public + login) | Added `panels` namespace to `i18n-strings.js` — ~450 EN/RU/KK strings covering headings, buttons, filter chips, table headers, empty states and toasts for 15 admin panels (Analytics, Audit, Awards, BOQ, Bidding, Corrigenda, Engagements, Evaluation, LiveAuctions, MFA, Masters, Permissions, Reports, TenderBuilder, VendorIntel). 21 of 22 admin panels now use `useI18n` | Wave 42a
43 | Delivered | UX / Mobile | Mobile-first responsive layout across top pages | Home@375px now renders at exact viewport (was 421 overflow) via responsive stat cards + `overflow-x-hidden`. AdminDashboard's 22-tab bar collapses into a mobile `<select>` on md-, header buttons stack + adaptive text sizes. Every admin function reachable at 375/768 viewport with zero horizontal scroll | Wave 42b
44 | Delivered | Procurement | Scheduled Pre-Bid Meeting rooms (video + invitees + minutes) | New `/api/v1/meetings` router with dual provider (Jitsi iframe by default, Zoom via S2S OAuth for enterprise). Admin MeetingsPanel + shared MeetingRoom.jsx. RSVP-style invitee list, minutes upload, cancel flow | Wave 41a + 41b
45 | Delivered | Bidding | L1 (lowest-price) auto-comparison for mid-value tenders | New `/api/v1/comparison/l1/{notice_ref}` — automatic ranking of commercial bids per notice with tie-break rules, exposed on admin L1ComparisonPanel | Wave 41a
46 | Delivered | Bidding | Live Reverse Auction room with masked identities, auto-bid, price floor, anti-snipe | New `/api/v1/reverse-auctions/*` router · masked `Bidder A/B/C…` aliases · min-decrement + hard floor enforced · anti-snipe extends close time on last-second bids · auto-bid cascade lets pre-armed bidders undercut competitors automatically. Admin LiveAuctionsPanel + public `/vendor/auction/:aid` room with 2s polling | Wave 40
47 | Delivered | Taxonomy | UNSPSC / standardised product & service classification | New `/api/v1/taxonomy/*` router + curated UNSPSC-lite seed (87 nodes across 23 segments: Construction, Medical, IT/Telecom, Professional Services, Utilities, Facilities, Education). Search + tree + lookup-chain endpoints. Idempotent startup seed | Wave 40 · products/BOQ can now be tagged
48 | Delivered | Procurement | Formal corrigendum / amendment publisher for published notices | New `/api/v1/notices/{ref}/corrigenda` router — auto-numbered, deadline auto-update on parent notice, public banner on Notice Detail, admin CorrigendaPanel with withdraw | Wave 39
49 | Delivered | Bidding | Two-cover / split-envelope submission — technical clearance before commercial visibility | New `/bids/{id}/technical-clear` + `/financial-open`; `_redact_commercial()` strips price and commercial docs for tech-only viewers or before financial open | Wave 39
50 | Delivered | Post-Award | Auto-generated Purchase Order, SLA, and Contract on bid award | New `/api/v1/awards/*` router — 3 WeasyPrint PDFs (PO/SLA/Contract) drafted on award, stored in `award_documents`, downloadable by admin + awarded vendor, admin AwardsPanel with regenerate | Wave 39 · PMC-PO-YYYY-##### numbering
51 | Delivered | Evaluation | Technical vs commercial evaluators segregated (role firewall) | `tech_evaluator` role sees redacted bids (price + commercial notes + commercial documents stripped); commercial envelope gated by explicit `financial-open` after `technical-clear` | Wave 39 · supersedes earlier planned row
52 | Planned | Procurement | Direct-Purchase value-threshold gate | Config flag on notice/product so low-value catalog items skip full tender workflow and issue a direct PO | Roadmap · P2
53 | Planned | Taxonomy | UNSPSC picker widget in Product Catalog + BOQ Builder + registration scopes | Backend + seed shipped in Wave 40; frontend picker widgets still to be attached to product/BOQ/registration edit forms | Roadmap · P2
54 | Planned | Notifications | Live push notifications on mobile | Firebase/APNs plumbing scaffolded; waiting for `google-services.json` + APNs auth key | Blocked · P1
55 | Planned | Emails | Real transactional email dispatch | Currently console-logged; needs PMC-managed Resend key | Blocked · P2
56 | Planned | Compliance | Live KYC provider integration | Stubbed logic in place + pre-bid gate wired; awaiting `KYC_BASE_URL` and `KYC_API_KEY` | Blocked · P1
57 | Planned | Deployment | Native AWS Phase 2 migration (Postgres RLS, S3, Cognito, Fargate) | MongoDB + FastAPI on Managed for MVP; portability was a design constraint | Roadmap · P2

## Summary
PMC Managers v2 — Delivery status
Generated at | 2026-08-12T02:16:10.892168+00:00
Total scope items | 57
Delivered | 50 | 88%
Partial | 1 | 2%
Planned | 6 | 11%