## Bug Tracker
Bug ID | Title | Module | Severity | Status | Fix Approach | Wave | Ship / Notes
1 | Clone as draft error 500 | Tender Builder | P0 | FIXED | order field auto-assigned | Shipped v5 | Prod live
3 | Bidding Ops button logs out user | Bidding Ops | P0 | FIXED | Promise.allSettled | Shipped v5 | Prod live
4 | Blank form download PDF fails | Vendor Invites | P1 | FIXED | reportlab fallback | Shipped v5 | Prod live
8 | Invite Vendor not working | Vendors | P1 | CONFIRMED WORKING | User confirmed 26-Aug | N/A | No action
9 | Vendor Add & Fill Full Form 'undefined' toast | Vendors | P1 | FIXED | Defensive undefined fallback | Shipped v5 | Prod live
11 | L1 Comparison Run hangs | L1 Comparison | P0 | FIXED | 45-sec Promise.race timeout | Shipped v5 | Prod live
13 | Masters tab hangs | Masters | P0 | FIXED | Promise.allSettled | Shipped v5 | Prod live
14 | Escrow joint account created without officer info | Escrow | P1 | FIXED | Strict role + email uniqueness | Shipped v6 | Prod live
16 | Budget accepts negative numbers | Notices/Budget | P1 | FIXED | NoticeIn budget_amount ge=0 | Shipped v6 | Prod live
55 | Duplicate of #14 | Escrow | P1 | FIXED | See Bug 14 | Shipped v6 | Duplicate
5 | Notice creation as madhavi shows 'undefined' | Notices (Admin) | P1 | FIXED | reviewer.create=True + defensive notice_ref + role-aware publish | READY v10/v14 | In this zip
22 | Notices form retains previous details | Notices | P2 | FIXED | Full form reset on success | READY v10/v14 | In this zip
23 | Unclear validation toast (10 char min) | Notices Form | P2 | FIXED | Explicit 'Title 3+ chars, Description 10+ chars' | READY v10/v14 | In this zip
24 | Publish checkbox disabled for Master Admin | Notices (Admin) | P1 | FIXED | isMasterAdmin gate | READY v10/v14 | In this zip
46 | Nudge Stale Drafts unclear success | Registrations | P1 | FIXED | Three-branch toast (no drafts / none stale / count) | READY v10/v14 | In this zip
50 | 'clarify recorded' typo + wrong verb | Registrations | P1 | FIXED | Verb mapping | READY v10/v14 | In this zip
28 | Bulk Invite CSV — page blanks / signs out | Vendors — Bulk Invite | P0 | FIXED | Defensive try/catch in submit + ErrorBoundary at root | READY v10/v14 | In this zip
36 | Portal hangs on Audit click | Audit | P1 | PARTIAL | Root ErrorBoundary catches crashes; pagination still needed for full fix | READY v10/v14 | Partial in zip
39 | Generate Award Report page hangs | Evaluation / Awards | P0 | PARTIAL | Root ErrorBoundary catches crashes; PDF-timeout guard still needed | READY v10/v14 | Partial in zip
52 | Screen goes blank after bulk invite (dup of 28) | Vendors — Bulk Invite | P0 | FIXED | See Bug 28 | READY v10/v14 | Duplicate
57 | Screen goes blank after award report (dup of 39) | Awards & POs | P0 | PARTIAL | See Bug 39 | READY v10/v14 | Duplicate
58 | Screen goes blank across flows, requires re-login | General | P0 | FIXED | React ErrorBoundary at root — session preserved on crash | READY v10/v14 | In this zip
43 | Reverse auction Start button doesn't go live | Reverse Auctions | P1 | FIXED | Clearer error msg naming the specific gate (needs 2+ participants) | READY v10/v14 | In this zip
44 | Reverse auction Close button doesn't close | Reverse Auctions | P1 | FIXED | Clearer error msg + reject close-on-draft | READY v10/v14 | In this zip
51 | No notifications sent after nudging stale drafts | Notifications | P1 | FIXED | send-reminders now inserts admin notification per email sent | READY v10/v14 | In this zip
2 | New BOQ template not visible after submission | BOQ Templates | P1 | PARTIAL | Backend list now limits+sorts; QA to re-verify (may be old browser cache) | READY v10/v14 | Retest needed
12 | New BOQ contract not showing in list | BOQ Contracts | P1 | PARTIAL | Backend list capped at 500; retest with hard refresh | READY v10/v14 | Retest needed
19 | New package shows created msg but not in list | Packages | P1 | OPEN | Backend + frontend look correct on inspection; may be a caching bug. Reproduce with QA | Wave A2 | Retest first
30 | Newly activated vendor not appearing in Vendors table | Vendors | P1 | OPEN | approve_and_create_vendor sets tenant_id — should work. Retest with QA | Wave A2 | Retest first
35 | Product catalog created but not in table | Product Catalog | P1 | OPEN | reload() runs; suspect browser cache. Add cache-buster query param | Wave A2 | Frontend
37 | Duplicate of Bug 19 | Packages | P1 | OPEN | See Bug 19 | Wave A2 | Duplicate
42 | New reverse auction not listed as draft | Reverse Auctions | P1 | OPEN | Backend + frontend look correct; may be status filter or cache. Retest | Wave A2 | Retest first
45 | Rejected company not shown in Rejected list | Registrations | P1 | OPEN | Backend admin_list filters correctly. Verify status enum casing | Wave A2 | Retest first
25 | Withdrawn corrigenda still visible as active | Corrigenda / Notices | P1 | OPEN | Public list already filters is_active=True; admin list intentionally shows all with opacity. May be a UX confusion — clarify with QA | Wave C2 | Retest / clarify
26 | Corrigenda status not updated after Withdraw | Corrigenda | P1 | OPEN | See Bug 25 | Wave C2 | Retest / clarify
60 | Corrigendum still visible after withdrawing (dup of 25) | Corrigenda | P1 | OPEN | See Bug 25 | Wave C2 | Duplicate
6 | Vendor mailing address error persists | Vendor Registration | P1 | OPEN | SectionB/C validation; needs QA screenshot of exact field | Wave D2 | Awaiting repro
27 | Supplier Approve/Reject/Clarify actions not saved | Registrations | P1 | OPEN | Backend updates correctly; frontend reload should show. Retest | Wave D2 | Retest first
29 | Replace Registration Template — undefined toast | Vendors | P1 | OPEN | Backend response missing template_name in some paths; retest | Wave D2 | Retest first
47 | Can navigate past identity section without required fields | Vendor Registration | P1 | OPEN | Add section-level validation gate in wizard | Wave D2 | Frontend
48 | Unable to download blank registration form | Vendor Registration | P1 | OPEN | Likely dup of Bug 4 (fixed). QA to verify | Wave D2 | Retest / dup?
7 | Resume link not sent to email despite success msg | Vendor Registration / Email | P1 | OPEN | Verify EMAIL_KEY env var propagation to Docker | Wave E | Backend
15 | AI Bid Anomaly score/deviation blank | Dashboard | P2 | OPEN | Add default 'no anomalies' state | Wave E | Backend + frontend
17 | Error clicking 'Review document' from DocuSign email | DocuSign | P1 | OPEN | DocuSign URL expiry — add retry | Wave E | Backend
20 | Check status token — no error for invalid token | Public Landing | P2 | OPEN | Show toast on invalid token | Wave E | Frontend
21 | Login shows console error | Login | P2 | OPEN | Need actual console error from QA | Wave E | Investigate
31 | Localization incomplete | i18n | P2 | OPEN | Audit i18n JSON files | Wave E | Frontend
32 | Profile image not shown after re-login | Profile | P1 | OPEN | TopBar reload on route change | Wave E | Frontend
33 | Missing email/mobile validation across forms | Forms (general) | P2 | OPEN | Zod/yup validation | Wave E | Frontend
34 | Product catalog save doesn't persist | Product Catalog | P1 | OPEN | May be dup of Bug 35 caching | Wave E | Retest / dup?
38 | Tender Builder content doesn't update on tab switch | Tender Builder | P1 | OPEN | Reset activeTemplate on tab change | Wave E | Frontend
40 | L1 Comparison dropdown empty | L1 Comparison | P1 | OPEN | Filter for awarded bids | Wave E | Frontend
41 | Regenerate documents doesn't work | Awards & POs | P1 | OPEN | Add confirmation + version docs | Wave E | Backend
49 | Save snapshot to repo — JSON parsing error | Stakeholder Reports | P2 | OPEN | Wrap in try/catch, return JSON error | Wave E | Backend
54 | Cancelled meeting still visible | Meetings | P1 | OPEN | Add filter to hide cancelled by default | Wave E | Backend + frontend
56 | Rubric saved with values > max | Evaluation | P1 | OPEN | Server-side + client-side range check | Wave E | Backend + frontend
F1 | Trainee Handbook out-of-date | Docs | P2 | OPEN | Rewrite missing chapters | Wave F | Docs
G1 | Escrow dual-signature not enforced — same login can sign both | Escrow | P0-Gov | OPEN | Enforce email + user_id != between signers | Wave G | Backend
G2 | COI not cross-checked against committee membership | Evaluation / Committee | P0-Gov | OPEN | Block score submission if COI declaration missing | Wave G | Backend
G3 | Two access-control systems (Permissions vs Level) | Governance | P1 | OPEN | Consolidate or clarify in handbook | Wave G | Docs + Backend
G4 | Stakeholder Reports doesn't match description | Reports | P1 | OPEN | Rename module or build described reports | Wave G | Product decision
G5 | Reverse Auction DRAFT exposes public link | Reverse Auctions | P1 | OPEN | Hide bidder-URL until status=live | Wave G | Frontend + backend

## Summary
Status | Count | Notes
FIXED / SHIPPED | 20 | Live in prod or in this deploy batch
PARTIAL | 4 | Root cause mitigated (ErrorBoundary etc.), full fix pending retest
OPEN | 33 | Awaiting deploy of v10/v14 + QA retest OR needs more repro info
Deploy plan
1. Deploy backend-v10-waves-abcd.zip to EB
2. Upload frontend-v14-waves-abcd.zip to S3 + CloudFront /*
3. QA retest bugs marked 'READY v10/v14'
4. Confirm bugs in Wave A2/C2/D2 with QA — many may already be fixed
5. Tackle Wave E (16 remaining) + Wave F/G in next sprint