## Bug Tracker
Bug ID | Title | Module | Severity | Status | Fix Approach | Wave | Ship / Notes
1 | Clone as draft error 500 | Tender Builder | P0 | FIXED | order field auto-assigned in tender_templates.create_from_master | Shipped v5/v10 | Prod live
3 | Bidding Ops button logs out user | Bidding Ops | P0 | FIXED | Promise.allSettled in BiddingOpsPanel.load — non-admin 403s no longer break chain | Shipped v5/v10 | Prod live
4 | Blank form download PDF fails | Vendor Invites | P1 | FIXED | reportlab fallback PDF in vendor_invites.download_registration_template | Shipped v5/v10 | Prod live
5 | Notice creation as madhavi shows 'undefined' | Notices (Admin) | P1 | FIXED | permissions.py DEFAULT_MATRIX reviewer.create=True; NoticesPanel defensive notice_ref + role-aware publish checkbox | READY v8/v12 | In this zip
8 | Invite Vendor not working | Vendors | P1 | CONFIRMED WORKING | User confirmed 26-Aug — email working | N/A | No action
9 | Vendor Add & Fill Full Form 'undefined' toast | Vendors | P1 | FIXED | Defensive undefined fallback in AdminVendorCreate.submit | Shipped v5/v10 | Prod live
11 | L1 Comparison Run hangs | L1 Comparison | P0 | FIXED | 45-sec Promise.race timeout in L1ComparisonPanel.run | Shipped v5/v10 | Prod live
13 | Masters tab hangs | Masters | P0 | FIXED | Promise.allSettled in MastersPanel.load | Shipped v5/v10 | Prod live
14 | Escrow joint account created without officer info | Escrow | P1 | FIXED | escrow.py strict role + email uniqueness validation | Shipped v6 | Prod live
16 | Budget accepts negative numbers | Notices/Budget | P1 | FIXED | NoticeIn budget_amount ge=0 + frontend min='0' + NaN guard | Shipped v6/v11 | Prod live
24 | Publish checkbox disabled for Master Admin | Notices (Admin) | P1 | FIXED | v12 gates disabled state on isMasterAdmin (=me.role==='admin') | READY v8/v12 | In this zip
55 | Duplicate of #14 (Escrow blank joint account) | Escrow | P1 | FIXED | See Bug 14 | Shipped v6 | Duplicate
2 | New BOQ template not visible after submission | BOQ Templates | P1 | OPEN | Investigate tenant_id scoping on boqs.list_boq_templates; verify BOQTemplatesTab calls onReload correctly after boqApi.createTemplate | Wave A | Backend + frontend
12 | New BOQ contract not showing in list | BOQ Contracts | P1 | OPEN | Investigate contract_ref generation, tenant_id filter on contracts list; add cache-bust | Wave A | Backend
19 | New package shows created msg but not in list | Packages | P1 | OPEN | createPackage returns 201 but load() may query wrong status. Force reload with 'all' filter, ensure default status='backlog' | Wave A | Frontend
30 | Newly activated vendor not appearing in Vendors table | Vendors | P1 | OPEN | vendors.py list default filter may exclude 'pending_verify'. Add explicit status filter UI | Wave A | Backend + frontend
35 | Product catalog created but not in table | Product Catalog | P1 | OPEN | ProductCatalogPanel.reload() runs after save, but if is_active default differs. Check product_id vs id normalization | Wave A | Frontend
37 | Package created but not in table (dup of #19) | Packages | P1 | OPEN | See Bug 19 | Wave A | Duplicate
42 | New reverse auction not listed as draft | Reverse Auctions | P1 | OPEN | reverseAuctionApi.create returns id, but list() may not include it. Check tenant scoping in auction_live.list_reverse_auctions | Wave A | Backend
45 | Rejected company not shown in Rejected list | Registrations | P1 | OPEN | adminApi.listRegistrations({status:'rejected'}) — verify backend accepts this filter. Status may be stored as 'rejected' vs 'REJECTED' | Wave A | Backend
50 | Draft not shown in needs_clarification tab; typo 'clarify recorded' | Registrations | P1 | OPEN | Backend: /decision endpoint saves status='needs_clarification' but list filter case mismatch. Fix toast text 'clarify recorded' → 'clarification recorded' | Wave A | Backend + frontend
28 | Bulk Invite CSV — page goes blank or signs out | Vendors — Bulk Invite | P0 | OPEN | BulkInviteModal.submit lacks catch on 403/500 → unhandled promise rejection. Wrap in try/catch + toast; ensure CSRF token present | Wave B | Frontend
39 | Generate Award Report page hangs | Evaluation / Awards | P0 | OPEN | Long-running backend call needs Promise.race timeout + spinner; likely PDF generation timeout | Wave B | Backend + frontend
52 | Screen goes blank after bulk invite (dup of 28) | Vendors — Bulk Invite | P0 | OPEN | See Bug 28 | Wave B | Duplicate
57 | Screen goes blank after Generate Award Report (dup of 39) | Awards & POs | P0 | OPEN | See Bug 39 | Wave B | Duplicate
58 | Screen goes blank across flows, requires re-login | General | P0 | OPEN | Add React error boundary at root; on unhandled rejection show toast + preserve auth. Root cause: unhandled thrown errors in async handlers | Wave B | Frontend
36 | Portal hangs on Audit click | Audit | P1 | OPEN | AuditPanel probably paginating over all audit_events. Add server-side pagination + limit=100 | Wave B | Backend + frontend
25 | Withdrawn corrigenda still visible as active | Corrigenda / Notices | P1 | OPEN | corrigenda.py withdraw endpoint sets is_active=False but the public notice detail still shows. Fix: filter public /notices/{ref} to exclude is_active=False corrigenda | Wave C | Backend
26 | Corrigenda status not updated after Withdraw | Corrigenda | P1 | OPEN | CorrigendaPanel refreshes list after withdraw, but item still shows Withdraw btn if is_active isn't returned. Confirm response body includes is_active | Wave C | Backend + frontend
43 | Reverse auction Start button doesn't go live | Reverse Auctions | P1 | OPEN | auction_live.start endpoint may not set status='live' atomically. Add explicit status update + return updated doc | Wave C | Backend
44 | Reverse auction Close button doesn't close | Reverse Auctions | P1 | OPEN | Similar to 43 — close endpoint status update | Wave C | Backend
60 | Corrigendum still visible after withdrawing (dup of 25) | Corrigenda | P1 | OPEN | See Bug 25 | Wave C | Duplicate
6 | Vendor mailing address error persists after entered | Vendor Registration | P1 | OPEN | SectionB/C validation runs on stale state. Force controlled input + trim; validate mailing address separately | Wave D | Frontend
27 | Supplier Approve/Reject/Clarify actions not saved | Registrations | P1 | OPEN | registrations.decide endpoint may return 200 but status not updated. Investigate _out() + audit_log ordering | Wave D | Backend
29 | Replace Registration Template — 'undefined' toast + no template name | Vendors | P1 | OPEN | vendor_invites.replace_template response doesn't include template_name. Add fallback in frontend toast | Wave D | Backend + frontend
46 | Nudge Stale Drafts shows success but incorrect | Registrations | P1 | OPEN | send-reminders returns reminded=0 but toast shows success. Show clearer message when no drafts qualify | Wave D | Frontend
47 | Can navigate past identity section without filling required fields | Vendor Registration | P1 | OPEN | Section navigation should validate current section before allowing next. Add required-field guard in Section A/B | Wave D | Frontend
48 | Unable to download blank registration form (dup of #4?) | Vendor Registration | P1 | OPEN | Verify with QA if this differs from Bug 4 which was fixed | Wave D | Investigate
51 | No notifications sent after nudging stale drafts | Notifications | P1 | OPEN | send-reminders should push notifications alongside email. Add notify.push_admin() call | Wave D | Backend
7 | Resume link not sent to email despite success message | Vendor Registration / Email | P1 | OPEN | Resend integration — verify EMAIL_KEY env var propagates to Docker container. Add error log + toast on failure | Wave E | Backend
15 | AI Bid Anomaly score/deviation blank | Dashboard | P2 | OPEN | bids_ai_compare.anomaly_check may return empty. Add default 'no anomalies detected' state + explain what it checks | Wave E | Backend + frontend
17 | Error clicking 'Review document' from DocuSign email | DocuSign | P1 | OPEN | Docusign embedded signing URL expiry. Add error page + retry | Wave E | Backend
20 | Check status token — no error for invalid token | Public Landing | P2 | OPEN | registrations.status endpoint returns 404 but frontend swallows. Show toast on invalid token | Wave E | Frontend
21 | Login shows console error | Login | P2 | OPEN | Need actual console error text from QA. Likely a benign CORS or 401 preflight | Wave E | Investigate
22 | Notices form retains previous details | Notices | P2 | OPEN | NoticesPanel setDraft resets title+description only. Full reset needed | Wave E | Frontend
23 | Unclear validation toast (10 char min) | Notices Form | P2 | OPEN | Change toast to explicit 'Title needs 3+ chars, Description needs 10+ chars' | Wave E | Frontend
31 | Localization incomplete | i18n | P2 | OPEN | Audit /app/frontend/src/i18n/*.json — fill missing keys in ru/kz | Wave E | Frontend
32 | Profile image not shown after re-login | Profile | P1 | OPEN | admin/auth/me returns avatar_data_url but frontend may cache stale. Verify TopBar reloads on route change | Wave E | Frontend
33 | Missing email/mobile validation across forms | Forms (general) | P2 | OPEN | Add zod/yup validation to Section A/B/C — email regex + phone digits-only | Wave E | Frontend
34 | Product catalog save doesn't persist | Product Catalog | P1 | OPEN | PATCH /products/{id} returns 200 but 'Saved' toast fires without reload. Add reload() call | Wave E | Frontend
38 | Tender Builder content doesn't update on tab switch | Tender Builder | P1 | OPEN | State not cleared between Tender/RFP/RFQ tabs. Reset activeTemplate on tab change | Wave E | Frontend
40 | L1 Comparison dropdown empty | L1 Comparison | P1 | OPEN | Filter for notices with awarded bids. Verify status filter | Wave E | Frontend
41 | Regenerate documents doesn't work under Awards & POs | Awards & POs | P1 | OPEN | awards.regenerate endpoint returns 200 but no visible change. Add version + timestamp on regenerated docs | Wave E | Backend
49 | Save snapshot to repo — JSON parsing error | Stakeholder Reports | P2 | OPEN | reports.snapshot returns non-JSON on error. Wrap in try/catch, return JSON error body | Wave E | Backend
54 | Cancelled meeting still visible | Meetings | P1 | OPEN | meetings.cancel sets status='cancelled' but list default doesn't filter. Add filter + hide by default | Wave E | Backend + frontend
56 | Rubric saved even with values > max | Evaluation | P1 | OPEN | evaluations.save_rubric doesn't validate weights sum. Add server-side + client-side range check | Wave E | Backend + frontend
F1 | Trainee Handbook out-of-date (missing chapters) | Docs | P2 | OPEN | Rewrite chapters for Permissions, Engagements, Help Requests, Portal Branding, AI features, role-to-tab map | Wave F | Docs
G1 | Escrow dual-signature not enforced — same login can sign both | Escrow | P0-Governance | OPEN | Enforce at escrow.create_account: pmc_officer.email != escrow_officer.email AND neither login should hold both roles. Extend to sign-off: verify signer's user_id ≠ other officer's user_id | Wave G | Backend
G2 | COI not cross-checked against committee membership | Evaluation / Committee | P0-Governance | OPEN | Before evaluations.submit_scores: check db.coi_declarations for that committee_member + notice_ref. Block if missing | Wave G | Backend
G3 | Two access-control systems (Permissions vs Level) — no defined relationship | Governance | P1 | OPEN | Document: Permissions matrix governs actions; Level is legacy from Wave 7 hierarchy. Consolidate or clarify in handbook | Wave G | Docs + Backend
G4 | Stakeholder Reports doesn't match description | Reports | P1 | OPEN | Rename module or build the described procurement reports | Wave G | Product decision
G5 | Reverse Auction DRAFT exposes public link | Reverse Auctions | P1 | OPEN | Hide bidder-URL until status='live'; verify draft link is 404 if visited before start | Wave G | Frontend + backend

## Wave Summary
Wave | Theme | Bug count | Deploy plan
Shipped | Bugs 1, 3, 4, 8, 9, 11, 13, 14, 16, 55 — live on prod | 10 | Already live at www.pmcmanagers.com
v8/v12 | Bug 5 (madhavi notice) + Bug 24 (publish checkbox) + Mongo/env guards + _temp_downloads stripped | 2 | In v8/v12 zips — deploy per README included
Wave A | Created-but-not-in-list pattern — 9 bugs (2, 12, 19, 30, 35, 37, 42, 45, 50) | 9 | Next wave — backend list filter audits + frontend reload() adds
Wave B | Blank-screen / re-login — 6 bugs (28, 36, 39, 52, 57, 58) | 6 | React error boundary + Promise.allSettled where missing
Wave C | Corrigenda withdraw + notice lifecycle — 5 bugs (25, 26, 43, 44, 60) | 5 | Backend status-update fixes
Wave D | Vendor + registration + supplier actions — 7 bugs (6, 27, 29, 46, 47, 48, 51) | 7 | Backend + frontend validation batch
Wave E | Validations, i18n, misc — 15 bugs | 15 | Small individual fixes; can ship rolling
Wave F | Handbook rewrite | 1 | Docs sprint — after all code fixes
Wave G | Governance (dual-sig enforcement, COI, RBAC) — 5 items | 5 | Investor-critical before code review

## Structural Observations
Module / Screen | Recommendation
Dashboard | AI Bid Anomaly Check — add one-line description above control + show what was flagged after run
Dashboard | Pipeline Funnel + Top-Priced Bids — make clickable → drill through to filtered Bidding Ops
Registrations | List view: surface submission_date; Nudge Stale Drafts — show threshold + preview count
Vendors | Bulk Invite: link sample CSV; warn about mid-registration template replacement; add status filter for 'pending_verify'
Notices (admin) | Add search/filter by status, closing date, template-linked flag; TEMPLATE LINKED tag → jump to template
Corrigenda | Require reason on Withdraw; log distinctly in Audit
Tender Builder | 'All kinds' view or Kind column; show last-edited timestamp + revision indicator
Bidding Ops — Committee | Chairperson dropdown populate from selected Members only; validate quorum ≤ #members; replace Ctrl/Cmd multi-select with checkbox list; edit/dissolve committee actions; resend invite for pending externals
Escrow | Aging indicator + SLA alert threshold; filter transactions by vendor/bid/status; reconciliation summary vs bank balance
Evaluation | Add rationale note next to non-obvious role/permission combos
L1 Comparison | Empty state: state count + why excluded; surface active ranking rule; add PDF/Excel export
Awards & POs | Add confirmation on Regenerate + version documents
DocuSign | Envelope Log — flag most recent/authoritative envelope per doc type per award
Reverse Auctions | Post-auction summary/report; bid history; winning price
Meetings | Require notice_ref when scheduling OR clearly mark meetings as internal/not tender-linked
Vendor Intel | Legend for WL flag; clarify anonymized entry
BOQ & Contracts | Contracts sub-tab needs same review — export, filtering, version history
Masters / Permissions | Add/Clone role for org-specific narrower roles; extend matrix to cover tab-level visibility; show last-modified metadata on Permissions screen
Packages | Empty-column messages consistent with rest of app
Audit | Add filters by actor/type/date range
Engagements | Date/aging columns for receivables; require cancellation reason (Registrations pattern); link buyer name → vendor record
Product Catalog | Log price-change history per product
Help Requests | Requester identity, priority, category, assignee, aging fields
Portal Branding | Live preview + logo history + broader theming (color, favicon)